## Instructions
Test Design & Execution Forecast Template
How to use
1) Fill assumptions in Inputs sheet
2) Add planned test cases in Test_Plan
3) Track execution in Execution_Tracking
4) Review KPIs and forecast in Forecast_Summary
Tip: Keep Test IDs consistent across Test_Plan and Execution_Tracking.

## Inputs
Input | Value | Notes
Planned test cases | 120 | Total number of test cases expected
Avg design hours per test | 1.5 | Average effort to design one test case
Avg execution hours per test | 0.75 | Average effort to execute one test case
No. of test designers | 2 | People available for design
Design hours per designer/day | 6 | Net productive hours per day
No. of test executors | 3 | People available for execution
Execution hours per executor/day | 6 | Net productive hours per day
Re-test uplift % | 0.15 | Expected re-test effort as a fraction
Contingency % | 10% | Extra allowance for uncertainty
Total design hours |  | Calculated
Total execution hours |  | Calculated
Forecast design days |  | Calculated
Forecast execution days |  | Calculated

## Test_Plan
Test ID | Feature | Test Scenario | Priority | Test Type | Complexity | Design Owner | Estimated Design Hours | Estimated Execution Hours | Design Status
TC-001 | Login | Valid login with MFA | High | Functional | Medium | Analyst A | 1.5 | 0.75 | Designed
TC-002 | Login | Invalid password lockout | High | Functional | Low | Analyst B | 1 | 0.5 | In Design
TC-003 | Checkout | Promo code with tax | Medium | Integration | High | Analyst A | 2 | 1 | Not Started

## Execution_Tracking
Test ID | Feature | Execution Status | Planned Exec Date | Actual Exec Date | Defect ID | Defect Severity | Re-test Required | Execution Owner | Notes
TC-001 | Login | Pass | 2026-03-30 | 2026-03-30 |  |  | No | Tester A
TC-002 | Login | Fail | 2026-03-30 | 2026-03-31 | BUG-1201 | High | Yes | Tester B | Account lock threshold mismatch
TC-003 | Checkout | Not Run | 2026-04-01 |  |  |  | No | Tester C | Blocked by env refresh

## Forecast_Summary
Forecast Summary
Metric | Value
Total Planned Test Cases
Designed Test Cases
Design Completion %
Executed Test Cases
Execution Completion %
Passed
Failed
Blocked
Pass Rate %
Open Defect Count
Forecast Design Days
Forecast Execution Days